## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
#1 |  | Initial selection | Initially the screen should display the option for Login and Registration for Admin,Doctor and Customer | Task | Create a login JSP which is integrated with the spring security . | critical | Shubham Srivastava | 2019-11-03 | 13/03/2019 | 4 |  | Done |  |  |  |  | critical | New Requirement
|  |  |  | Task | On clicking registration link it will be redirected to the registration forms of Customer,Admin and doctor |  | Saurabh Gidwani | 2019-11-04 | 13/03/2020 |  |  | Done
|  |  |  | Task | we have created a navigation bar which will redirect to the different registration forms. |  | Saurabh Gidwani | 2019-11-05 | 13/03/2019 |  |  | Done
|  | Customer Registration | As a customer when I clicks on the registration link, it should re-direct to registration form. | Task | Create a JSP for customer registration which will have all the necessary fields. | critical | Saurabh Gidwani | 14/03/2019 | 15/03/2019 | 3 |  | Done |  |  |  |  | critical | New Requirement
[5 empty] | On clicking Register button the form validates using JS . |  | Shivam Goel | 14/03/2019 | 15/03/2019
[5 empty] | After validation data is populated into the corresponding database. |  | Shivam Goel | 14/03/2019 | 15/03/2019
|  | Customer Registration | As a customer on Clicking 'Submit' should validate the datatype constraints for each field | Task | On submit JS validation is triggered | critical | Shivam Goel | 16/03/2019 | 17/03/2019 | 3 |  | Done |  |  |  |  | critical | New Requirement
|  | Customer Registration | As a customer if I am failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task | Add JS functionality to mark the unfilled field as red | critical | Shubham Srivastava | 17/03/2019 | 18/03/2019 | 2 |  | Done |  |  |  |  | critical | New Requirement
|  | Customer Registration | As a Admin i should be able to view the New Customers for registration | Task | Create a JSP page which retrives all the customer present in the database . | Critical | Shubham Srivastava | 19/03/2019 | 20/03/2019 | 2 |  | Done |  |  |  |  | Critical | New Requirement
|  | Credential Authentication | A registered Customer - is able click 'Login' link, after keying in 'Customer ID' & 'Password' field and get his credentials authenticated with the existing database entry. | Task | On entering 'Customer ID' & 'Password' the connection with the database is established | critical | Shubham Srivastava | 21/03/2019 | 22/03/2019 | 2 |  | Done |  |  |  |  | Critical | New Requirement
|  |  |  | Task | Now the 'Customer ID' will be verified from the database if it exists then the encrypted password is and the verified from the existing password in the database. |  | Vinayak Gupta | 21/03/2019 | 22/03/2019
|  |  |  | Task | On successful validation it would be redirected to the respective Dashboard |  | Saurabh Gidwani | 21/03/2019 | 22/03/2019
|  | Doctor Registration | As a doctor when I click on the registration link, it should re-direct to registration form. | Task | Create a JSP for doctor registration which will have all the necessary fields. | Critical | Vinayak Gupta | 22/03/2019 | 23/03/2019 | 3 |  | Done |  |  |  |  | Critical | New Requirement
|  |  |  | Task | On clicking Register button the form validates using JS . |  | Shivam Goel | 22/03/2019 | 23/03/2019
|  |  |  | Task | After validation data is populated into the corresponding database. |  | Shubham Srivastava | 22/03/2019 | 23/03/2019
|  | Doctor Registration | As a doctor on 'Submit' should validate the datatype constraints for each field | Task | On submit JS validation is triggered | critical | Shubham Srivastava | 23/03/2019 | 24/03/2019 | 3 |  | Done |  |  |  |  | critical
|  | Doctor Registration | As a doctor failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task | Add JS functionality to mark the unfilled field as red | Medium | Shivam Goel | 24/03/2019 | 25/03/2019 | 3 |  | Done |  |  |  |  | critical
|  | Doctor Registration | As a admin i should be able to view the New Doctors for registration | Task | Create a JSP page which retrives all the doctor present in the database . | critical | Shivam Goel | 25/03/2019 | 26/03/2019 | 2 |  | Done |  |  |  |  | critical
|  | Admin Registration | As a admin when I click on the registration link, it should re-direct to registration form. | Task | Create a JSP for Admin registration which will have all the necessary fields. | critical | Shivam Goel | 26/03/2019 | 27/03/2019 | 1 |  | Done |  |  |  |  | critical
[5 empty] | On clicking Register button the form validates using JS . |  | Saurabh Gidwani | 26/03/2019 | 27/03/2019
[5 empty] | After validation data is populated into the corresponding database. |  | Vinayak Gupta | 26/03/2019 | 27/03/2019
|  | Admin Registration | As a admin on 'Submit' should validate the datatype constraints for each field | Task | On submit JS validation is triggered | critical | Shivam Goel | 27/03/2019 | 28/03/2019 | 3 |  | Done |  |  |  |  | critical
|  | Admin Registration | As a admin if I am failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task | Add JS functionality to mark the unfilled field as red | Medium | Shubham Srivastava | 28/03/2019 | 29/03/2019 | 2 |  | Done |  |  |  |  | critical
#2 |  | Update Medicare Service Details | As a doctor i should be able to update the mandatory fields of the Medicare Service | Task# | Create a JSP form displaying previous values of fields Name,Amount and Description | critical | Shubham Srivastava |  |  | 3 |  | Done |  |  |  |  | critical
|  |  |  | Task | Send the updated details to Medical service controller class through model attribute service. |  | Saurabh Gidwani |  |  |  |  | Done
|  |  |  | Task | Save the model attribute in object of Medical service class and pass it to DAO layer through Service layer for update and save |  | Saurabh Gidwani |  |  |  |  | Done
|  |  |  | Task | Display a message through Javascript on successful submisson of Medical Service details. |  | Vinayak Gupta |  |  |  |  | Done
[5 empty] | Display/redirect to the JSP page containing all the updated Medical Services |  | Shubham Srivastava |  |  |  |  | Done
|  | View Medicare Service/ Doctor / Agent details | As a customer on Clicking the View button corresponding Medicare ID, it should list all the details of the Medicare services | Task | Create a JSP page listing all the Medicare Services and a view button corresponding to them | critical | Vinayak Gupta |  |  | 2 |  | Done |  |  |  |  | critical
|  |  |  | Task | Create a function in controller layer that will accept the Medicare Service ID provided by view button. |  | Vinayak Gupta |  |  |  |  | Done
|  |  |  | Task | Function will call a method in service and DAO layer that accepts ID as parameter and return the Medicare Service object, which is then passed as model attribute to the JSP. |  | Shubham Srivastava |  |  |  |  | Done
|  |  |  | Task | Create a JSP displaying details of Medicare Services in that object. |  | Saurabh Gidwani |  |  |  |  | Done
|  | View Medicare Service/ Doctor / Agent details | As a customer on clicking View Doctor, the page should list all the doctors available | Task | On clicking view doctor a function returning list of all the doctors is called | critical | Shivam Goel |  |  | 4 |  | Done | S |  |  |  | critical
|  |  |  | Task | The return list of doctors is added as a attribute and is passed to the JSP. |  | Shubham Srivastava |  |  |  |  | Done
|  |  |  | Task | Create a JSP displaying list of all available Doctors. |  | Vinayak Gupta |  |  |  |  | Done
|  | View Medicare Service/ Doctor / Agent details | By Clicking the Doctor Id, it should display all the details of the doctor | Task | Create a function in controller layer that will accept the Doctor ID provided by view button. |  | Saurabh Gidwani |  |  | 2 |  | Done |  |  |  |  | critical
[5 empty] | Function will call a method in service and DAO layer that accepts ID as parameter and return theDoctor object, which is then passed as model attribute to the JSP. |  | Shivam Goel |  |  |  |  | Done
[5 empty] | Create a JSP displaying details of Doctor in that object. | critical | Shubham Srivastava |  |  |  |  | Done | M
|  | Raise Checkup request | As a customer when I Click on Raise Checkup request link, it should redirect to the Request creation page | Task | Create a JSP form for getting the checkup request | Critical | Shubham Srivastava |  |  | 2 |  | Done |  |  |  |  | critical
|  |  |  | Task | On clicking the Request link a JSP form appears . |  | Saurabh Gidwani
|  | Raise Checkup request | As a customer i should be able to fill in the necessary fields, select date, doctor and Medicare service and submit the request | Task | On clicking the Raise request, a request associated to a particular doctor is created and saved in the corresponding database. |  | Vinayak Gupta |  |  | 3 |  | Done |  |  |  |  | critical
|  | Raise Checkup request | As a doctor i should be able to view the Checkup request and approve it | Task | create a request section where doctor is able to view the pending request from the customers. | critical | Shivam Goel |  |  | 2 |  | Done |  |  |  |  | critical
[5 empty] | On clicking the decline request button it hits the request controller which initiates the decline request method changes the status from the pending to rejected |  | Shivam Goel
|  |  |  | Task | On clicking the accept request button it hits the request controller which initiates the accept request method changes the status from the pending to accepted |  | Vinayak Gupta
|  | Update Test results | As a doctor on clicking the Checkup request ID, Doctor should have the option to update the test results | Task | On clicking the update result doctor controller initiates the update result method which returns the update JSP form. | critical | Shubham Srivastava |  |  | 3 |  | Done |  |  |  |  | critical
|  |  |  | Task | On clicking the save update report button it initiates the method save reports which saves the data into the database and redirect us to the reports JSP. |  | Shubham Srivastava
|  | View test results | As a customer on clicking the Checkup request ID, Doctor / consumer should be able to view the test results | Task | on clicking the view reports all the reports of corresponding customer/doctor will be displayed in tabular form. | Critical | Shivam Goel |  |  | 4 |  | Done |  |  |  |  | critical
|  | Admin/Customer/Doctor log off | Option to log off from the system. | Task | when we click logout button which hits the login controller which initiates the logout method and redirect us to the login page. |  | Saurabh Gidwani |  |  | 2 |  | Done |  |  |  |  | critical
Shubham Srivastava
Saurabh Gidwani
Shivam Goel
Vinayak Gupta